## Test Plan
Click Here For the PDF

## TestScenarios
Project Name | Foodpanda
Reference Document | FRS
Created By | Rokaiya Zaman Suthi
Creation Date | 15-01-2025
Approval Date | 15-01-2025
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the working of the "Login" functionality | P0 | 25
TS_002 |  | Validate the "Sign up" functionality | P0 | 19
TS_003 |  | Validate the "logout" functionality | P0 | 10
TS_004 |  | Validate the working of "Home page" functionality | P1 | 14
TS_005 |  | Validate the "Search bar" funcitonality | P1 | 20
TS_006 |  | Validate the functionality of "Delivery tracking" | P0 | 21
TS_007 |  | Validate the "Ordering overflow" functionality | P0 | 23
TS_008 |  | Validate the "Payment" functionality | P0 | 30
TS_009 |  | Validate the "Profile" functionality | P3 | 14
TS_010 |  | Validate the "Help center" functionality | P4
TS_011 |  | Validate the "Orders and reordering" functionality | P4

## TestCase
Product Name |  | Foodpanda | TC Start Date | 15-01-2025 | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Account | TC End Date | 19-01-2025 | TC Execution End Date | - - |  |  |  |  | PASS | 161
Epic |  |  | Test Case Developed By | Rokaiya Zaman Suthi | Browser (tested) | Yes |  |  |  |  | FAIL | 3
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  |  |  |  | NO Execution | 12
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 176
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproduching steps | Bugs Screenshot | Dev Comments | Final Status | Remarks
1 | Module | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'Foodpanda' 3. Go to the website. |  |  | Passed
2 |  |  | Sign up | Verify the Sign-Up page loads correctly | The Sign-Up form is displayed with fields like Name, Email, Password, and Phone Number. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
3 |  |  |  | Verify the user can successfully sign up with valid inputs | The account is created, and the user is redirected to the welcome or dashboard page. | Found as per expectation. | rokaiyasuchi150@gmail.com | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
4 |  |  |  | Verify an error message is displayed for missing mandatory fields | An error message is displayed, such as "This field is required." | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
5 |  |  |  | Verify an error message is displayed for invalid email format | An error message like "Please enter a valid email address" is shown | Found as per expectation. | rokaiyasuchi150gmail.com | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
6 |  |  |  | Verify an error message is displayed for weak passwords | An error message like "Password must be at least 8 characters long and include a combination of letters and numbers." | Found as per expectation. | 12345 | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
7 |  |  |  | Verify the user cannot sign up with an already registered email | An error message like "This email is already registered" is displayed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
8 |  |  |  | Verify the user receives a verification email after successful sign-up | A verification email is sent to the registered email address with a link or code to confirm the account. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
9 |  |  |  | Verify the user cannot log in without verifying their email | An error message like "Please enter a valid phone number" is displayed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
10 |  |  |  | Verify phone number validation during sign-up | An error message like "Please enter a valid phone number" is displayed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
11 |  |  |  | Verify password masking in the Password field | The characters are masked with dots or asterisks for security. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
12 |  |  |  | Verify the "Show Password" functionality works correctly | An error message like "You must agree to the terms and conditions to proceed" is displayed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
13 |  |  |  | Verify the terms and conditions checkbox is mandatory | An error message like "You must agree to the terms and conditions to proceed" is displayed. | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Not executed
14 |  |  |  | Verify the "Sign Up" button is disabled until all mandatory fields are filled | The "Sign Up" button remains disabled. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
15 |  |  |  | Verify the field placeholders provide clear guidance | Clear guidance is provided (e.g., "Enter your full name"). | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
16 |  |  |  | Verify error messages are displayed near the corresponding fields | Error messages are displayed close to the relevant fields. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
17 |  |  |  | Verify the tab order is logical on the Sign-Up form | The cursor moves in a logical order through the fields. | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
18 |  |  |  | Verify that passwords are encrypted when sent to the server | Passwords are sent in an encrypted format. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
19 |  |  |  | Verify the Sign-Up process works under heavy load | The Sign-Up process remains functional without delays or errors. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
20 |  |  |  | Verify the form submission time | Form submission is completed within 2-3 seconds. | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the account button in the right side on the above. 3.Click sign up button and give information then press continue. |  |  | Passed
22 |  |  | Log in | Verify the Login page loads successfully | The Login form with Email and Password fields is displayed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
23 |  |  |  | Verify the error message for invalid inputs | An error message like "Invalid email or password" is displayed. | Found as per expectation. | rokaiya@gmail | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
24 |  |  |  | Verify login functionality with a blank Email field | An error message like "Email is required" is displayed | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
25 |  |  |  | Verify login functionality with a blank Password field | An error message like "Password is required" is displayed | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
26 |  |  |  | Verify login functionality with an unregistered email | An error message like "Email not found" is displayed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
27 |  |  |  | Verify the password is masked when entered in the Password field | The password is masked with dots or asterisks. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
28 |  |  |  | Verify the "Show Password" functionality | The password is displayed in plain text and can be toggled back to masked. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
29 |  |  |  | Verify login functionality for locked accounts | An error message like "Your account is locked. Please contact support" is displayed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
30 |  |  |  | Verify successful login redirects to the correct page | The user is redirected to their dashboard or homepage. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
31 |  |  |  | Verify the "Forgot Password" functionality | The user is redirected to the password recovery page. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
32 |  |  |  | Verify the "Login" button is disabled until mandatory fields are filled | The "Login" button remains disabled until all mandatory fields are filled. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
33 |  |  |  | Verify the user can log in with valid inputs | The user is successfully logged in and redirected to the dashboard. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
34 |  |  |  | Verify the "Remember Me" checkbox functionality | The user's credentials are saved for future sessions. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
|  |  |  | Verify error messages are displayed near the corresponding fields | Error messages are displayed close to the relevant fields. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
35 |  |  |  | Verify the responsiveness of the Login page on different devices | The Login page adjusts to screen sizes without layout issues. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
36 |  |  |  | Verify passwords are encrypted when sent to the server | Passwords are transmitted in encrypted format. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
37 |  |  |  | Verify account lockout after multiple failed login attempts | The account is locked, and an error message like "Your account is locked due to multiple failed attempts" is displayed | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
38 |  |  |  | Verify session timeout after inactivity | The user is logged out automatically and redirected to the Login page. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
39 |  |  |  | Verify the Login process works under heavy load | The Login process remains functional without delays or crashes. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
40 |  |  |  | Verify the response time of the Login API | The API responds within 2-3 seconds. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
41 |  |  |  | Verify the tab order is logical on the log in form | The tab order should move sequentially from the username field to the password field, and then to the login button. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
42 |  |  |  | Verify logged-in user doesn’t log out by clicking the back button on the browsers tab | The user should remain logged in and be navigated to the previous page without being logged out. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
43 |  |  |  | Check logged in user should not log out on closing the browser | The user should remain logged in after reopening the browser if the session is set to persist. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
44 |  |  |  | Verify logged-in user copies the URL and pastes it into a new browser window, it should redirect to the login page | Pasting the URL into a new browser window should redirect to the login page if the user’s session is not active. | Found not as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. | click_screenshort |  | Failed
45 |  |  |  | Check login by google and all social options for login in the private window separately | Each social login option (e.g., Google) should work seamlessly in a private window, allowing the user to log in without errors. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. |  |  | Passed
47
48 |  |  | Home page | Verify the login screen will appear after clicking on a login link or login button. | Login screen appears as expected after clicking the login link/button. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
49 |  |  |  | Verify all login-related elements and fields are present on the login page | All fields and elements are present (username, password, login button, etc.). | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
50 |  |  |  | Verify that the size, color, and UI of different elements should match the specifications. | Size, color, and design match the given specifications. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
51 |  |  |  | Verify that the login page of the application is responsive and aligns properly on different screen resolutions and devices. | Login page adjusts and aligns correctly on all devices and screen resolutions. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
52 |  |  |  | Verify that the system rejects an invalid username. | System shows an error message and denies login. | Found as per expectation | R@kaiya zaman | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
53 |  |  |  | Verify that the system rejects an invalid password. | System shows an error message and denies login. | Found as per expectation | R@kaiya zaman | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
54 |  |  |  | Verify login page title. | Title is correct and matches the application’s specification. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
55 |  |  |  | After the user login page is open, the cursor should remain in the username text box by default. | Cursor is focused on the username field by default. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
56 |  |  |  | Verify that the password field correctly masks the entered password | Password field hides input using masking characters (e.g., dots/asterisks). | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
57 |  |  |  | Verify that the "Remember Me" checkbox retains the user's login information after logging out and reopening the page. | Checkbox retains login info after logout and reopening. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
58 |  |  |  | Verify that the login button is disabled when both fields (username and password) are empty | Login button remains disabled if fields are empty. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
46 |  |  |  | Verify that the "Forgot Password" link redirects to the correct password recovery page | Link correctly redirects to the password recovery page. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
59 |  |  |  | Verify that the login button is enabled once valid credentials are entered. | Login button enables only when valid credentials are entered. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
60 |  |  |  | Verify that the "Forgot Password" link redirects to the correct password recovery page. | Link correctly redirects to the password recovery page. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
61 |  |  |  | Verify that the system handles invalid email formats during login. | System shows an error message for invalid email formats. | Found as per expectation | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page |  |  | Passed
62 |  |  | Log out | Verify that the user can successfully log out of the system. | User is successfully logged out and redirected to the login page. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
63 |  |  |  | Verify that the "Log Out" button is visible when the user is logged in. | "Log Out" button is visible when the user is logged in. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
64 |  |  |  | Verify that the user is redirected to the login page after clicking the "Log Out" button. | Clicking "Log Out" redirects to the login page. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
65 |  |  |  | Verify that the session is terminated when the user logs out | User session is terminated upon logging out. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
66 |  |  |  | Verify that logging out from one device also logs out the user from other devices (if applicable) | The user remains logged in on other devices | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option | Click_screenshort |  | Failed
67 |  |  |  | Verify that the user is logged out after a period of inactivity (session timeout). | User is automatically logged out after inactivity, and redirected to the login page. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
68 |  |  |  | Verify that the "Log Out" button is disabled or hidden after the user logs out. | The "Log Out" button is disabled or hidden after logging out. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
69 |  |  |  | Verify that the "Remember Me" feature works correctly after the user logs out. | "Remember Me" feature retains login credentials after logout | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
70 |  |  |  | Verify that the user is asked for confirmation before logging out (if applicable). | User is prompted for confirmation before logging out (if applicable). | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
71 |  |  |  | Verify that the user can log out from the mobile version of the website or app. | User can log out from the mobile version of the website/app. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option |  |  | Passed
72 |  |  | Search Bar | Verify the search field is present and aligned. | The search field is visible and correctly aligned. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
73 |  |  |  | Verify whether placeholder text is added on search or not | Placeholder text is present in the search field. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify spelling and grammar should be correct for placeholder text. | Placeholder text is free from spelling and grammar errors. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify search icon is present on the field | A search icon is displayed within the search field. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify cursor should be present on click on the search icon. | The cursor is focused inside the search field after clicking the search icon. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify search is functional and generating the correct result for correct keywords or not by adding a valid search. | Correct results are displayed when valid keywords are entered. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify the search is working by adding keywords and pressing the Enter key on the keyboard | The search works when keywords are entered and the Enter key is pressed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify the search is working by adding keywords and on click on the search button | The search works when the search button is clicked after entering keywords. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify if the user can paste the keyword with the mouse | User can paste keywords into the search field using the mouse. | Found as per expectation. | suche | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify an error message displayed by entering invalid keywords in the search field and clicking the search button | An error message appears when invalid keywords are entered. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify an error message should display for blank input. | An error message appears when the search field is left empty. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify and observe how much time is required for getting the search result. | Search results are generated within an acceptable amount of time. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify a loader added if takes time to get the result. | A loader or spinner appears if the search takes time to generate results. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify the search result generated by the search in the correct order as per requirement | Search results are displayed in the correct order, as required. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify pagination added in case the search result goes on the number of pages | Pagination appears when the search results span multiple pages. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify whether pagination is accessible or not by clicking on the Next, Previous, and number. | Pagination buttons (Next, Previous, and number) are clickable and functional. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify whether suggestions are shown or not on adding a keyword to the search. | Suggestions are shown when a keyword is typed into the search field. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify the max and min range for the search keyword. | Search supports keywords within specified maximum and minimum lengths. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify whether auto-suggestion is shown on adding a keyword or not. | Auto-suggestions are displayed as the user types a keyword. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  |  | Verify whether related keywords are added to the search result or not. It should be added | Related keywords are displayed along with the search results. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar |  |  | Passed
|  |  | Delivery tracking | Verify that the delivery status updates in real-time as the order progresses. | Delivery status updates in real-time as the order progresses. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the system handles invalid order IDs gracefully. | Invalid order IDs result in an appropriate error message. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the estimated delivery time is calculated and displayed correctly | Estimated delivery time is calculated and displayed correctly. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the current location of the delivery is updated accurately based on GPS data. | Delivery location is updated accurately using GPS data. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that customers are notified of delivery delays. | Customers are notified of any delivery delays. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the recipient must confirm delivery upon receiving the package. | Recipient is required to confirm delivery upon receiving the package. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the delivery tracking system works under high server load. | The system performs well and tracks deliveries correctly under high load. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the system records and updates details for multiple delivery attempts | System records and updates details for multiple delivery attempts. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the delivery tracking integrates seamlessly with third-party logistics providers | The system does not integrate seamlessly with third-party logistics (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Not executed
|  |  |  | Verify the system handles partial deliveries for multi-item orders | System tracks partial deliveries for multi-item orders. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that only authorized users can access delivery tracking details | Only authorized users can view delivery tracking details. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that cancelled orders are removed from the tracking system | Cancelled orders are removed from the tracking system | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the system accurately tracks deliveries across different time zones | The system does not handle time zone differences accurately (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Not executed
|  |  |  | Verify that the delivery tracking system works seamlessly on mobile devices | Delivery tracking system works seamlessly on mobile devices. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that orders on hold due to pending payments or issues are reflected in tracking | Orders on hold (pending payments) are reflected in the tracking system. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that customers receive a notification when the delivery is completed | Customers are notified when their delivery is completed. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the delivery tracking system meets accessibility standards | The system meets accessibility standards for all users. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that returned items can be tracked through the system | Returned items can be tracked through the delivery system. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Verify that the delivery tracking system works across multiple platforms (web, mobile, desktop). | Delivery tracking works across web, mobile, and desktop platforms. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Passed
|  |  |  | Test if the user can set dietary preferences (e.g., vegetarian, vegan, gluten-free) | User cannot set dietary preferences (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment.After payment we can track the delivery |  |  | Not executed
|  |  | Ordering workflow | Verify that users can successfully log in to the ordering system. | Users can log in successfully with valid credentials. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can select a product and view its details | Users can select and view product details. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can add products to the cart. | Users can add products to their cart. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can update product quantities in the cart | Users can update product quantities in the cart. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can successfully proceed with the checkout | Users can proceed to checkout successfully. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the payment gateway processes payments correctly | Payments are processed correctly by the payment gateway | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users receive an order confirmation email after successful payment | Users receive a confirmation email after successful payment. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can view their past orders in the order history section | Users can view past orders in the order history section. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can successfully log out of the system. | Users can log out successfully. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system rejects invalid login credentials | System rejects invalid login credentials. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system handles searches with no matching results | System handles searches with no results appropriately. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users cannot add out-of-stock products to the cart | Users cannot add out-of-stock products to the cart. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the cart total is calculated correctly, including taxes and discounts | Cart total is calculated correctly, including taxes and discounts. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can remove items from the cart. | Users can remove items from the cart. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system rejects invalid payment details. | System rejects invalid payment details | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system handles session timeout appropriately | System handles session timeout appropriately. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can apply valid coupon codes and receive discounts | Users can apply valid coupons and receive discounts. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system rejects invalid or expired coupon codes | System rejects invalid or expired coupon codes. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can cancel an order before it is shipped. | Users can cancel an order before it is shipped. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | . Verify that cart data is synchronized across devices. | Cart data is synchronized across devices. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can track the status of their orders | Users can track the status of their orders. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that users can place orders without creating an account | Users cannot place orders without creating an account (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment | Click_screenshort |  | Failed
|  |  |  | Verify that users can search for products using the search bar. | Users can search for products using the search bar. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  | Payment | Verify that a payment is successfully processed when valid card details are entered. | Payment is processed successfully with valid card details. | Found as per expectation. | 4540 8754 7805 7890 | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that an error message is displayed when invalid card details are entered. | An error message is displayed for invalid card details | Found as per expectation. | 5689 8999 0011 6678 | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the payment fails with an appropriate message if the card has insufficient funds | Payment fails with an appropriate message for insufficient funds. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the payment is canceled successfully when the user clicks on the "Cancel Payment" button | Payment is canceled successfully when the "Cancel Payment" button is clicked. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that payment fails when an expired card is used. | Payment fails when using an expired card. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system allows multiple payment attempts after a failed transaction. | System allows multiple attempts after a failed transaction | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that a payment is processed successfully using a saved card. | Payment is processed successfully using a saved card | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the CVV entered is masked for security purposes | CVV is masked for security purposes | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that payment is processed successfully through a third-party wallet (e.g., PayPal, Google Pay). | Payment is processed successfully through third-party wallets | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system handles session timeouts during payment gracefully. | System handles session timeouts during payment gracefully. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that a payment receipt is generated and emailed to the user after a successful transaction | Receipt is generated and emailed after a successful transaction. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that payment fails when an incorrect CVV is entered. | Payment fails when an incorrect CVV is entered. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system allows partial payments if the option is available | System does not allow partial payments (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Not executed
|  |  |  | Verify that the system supports combining multiple payment methods (e.g., card and wallet). | System supports combining multiple payment methods. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system allows payment retry after a network failure | System allows payment retry after a network failure | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that payment processing time does not exceed the acceptable limit (e.g., 10 seconds). | Payment is processed within the acceptable time limit. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system prevents duplicate payments for the same order | System prevents duplicate payments for the same order. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system refunds the amount if a transaction fails after the amount is debited | Amount is refunded if a transaction fails after debit. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system accurately converts currency for international transactions. | System accurately converts currency for international transactions. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the user is auto-logged out after prolonged inactivity during the payment process | User is auto-logged out after prolonged inactivity during payment. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that the system processes payments made via bank transfer | System does not process payments via bank transfer (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that recurring payments for subscription services are processed automatically | Recurring payments for subscriptions are processed automatically. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify that payment fails when an incorrect OTP is entered during two-factor authentication | Payment fails when an incorrect OTP is entered during 2FA. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify spellings for the content on the pricing page are correct or not. | Spelling on the pricing page is correct. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Do not allow the user to purchase a plan without email verification. | User cannot purchase a plan without email verification. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify if the user can buy the plan successfully after email verification or not. | User can purchase a plan successfully after email verification. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify invoice generated on the purchase of a plan is accessible to the user or not. Sent in email or shown on Dashboard | Invoice is accessible via email or shown on the dashboard. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify user can download an invoice or not | User can download the invoice | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify the user login with social links can purchase a plan. | Users can purchase a plan after logging in with social links. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Passed
|  |  |  | Verify the expiry date for the purchased plan is shown on the profile or not | Expiry date for the purchased plan is not shown on the profile (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment |  |  | Not executed
|  |  | Profile | Test if the user can set the language preference to "English or Bangla". | User can set the language preference to "English" or "Bangla". | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Passed
|  |  |  | Test if the user can enable push notifications. | User can enable push notifications. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Passed
|  |  |  | Test if the user can update the delivery address. | User can update their delivery address | Found as per expectation. | Mirpur 2 | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Passed
|  |  |  | Test if the user can opt in to receive marketing emails | User can opt in to receive marketing emails. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Passed
|  |  |  | Test if the user can upload a new profile picture | User cannot upload a new profile picture (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Not executed
|  |  |  | Test if the user can switch to dark mode | User cannot switch to dark mode (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Not executed
|  |  |  | Test if the user can set their account to private | User cannot set their account to private (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Not executed
|  |  |  | Test if the user can enable location services | User can enable location services. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Passed
|  |  |  | Test if the user can update their personal details (name, phone number, etc.) | User can update personal details (name, phone number, etc.). | Found as per expectation. | Suche 0131649**** | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Passed
|  |  |  | Test if the user can limit data usage (e.g., enable "Low Data Mode") | User cannot enable "Low Data Mode" (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Not executed
|  |  |  | Test if the user can manage app permissions (e.g., camera, contacts, storage). | User can manage app permissions (camera, contacts, storage). | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Passed
|  |  |  | Test if the user can set a preferred method for receiving refunds (e.g., store credit, bank transfer) | User cannot set a preferred refund method (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Not executed
|  |  |  | Test if the user can request account deletion | User cannot request account deletion (expected failure). | Found not as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Not executed
|  |  |  | Test if the user can select a default payment method. | User can select a default payment method. | Found as per expectation. | None | 1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the profile option |  |  | Passed

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Foodpanda
Module Name | Account |  |  |  |  | Total No. | Status
Feature Name | Sing up Account & Account Login,Search bar,Ordering workflow,Delivery tracking,payment
Test Case Version | 1 |  |  |  |  | 161 | PASS
Written By | Rokaiya Zaman Suthi |  |  |  |  | 3 | FAIL
Executed By | Rokaiya Zaman Suthi |  |  |  |  | 12 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 161 | 3 | 12 | 0 | 176
Grand Total | 161 | 3 | 12 | 0 | 176
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 01
Issue: Verify logged-in user copies the URL and pastes it into a new browser window, it should redirect to the login page
Reproducing Steps:
1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue.
Env: Production.
Module: Login
Priority: Low
Severity: Minor
Screenshort
Expected: Pasting the URL into a new browser window should redirect to the login page if the user’s session is not active.
Responsible QA: Rokaiya zaman suthi
Bug Reporting
# SL 02
Issue: Verify that logging out from one device also logs out the user from other devices
Reproducing Steps:
1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5.click on the account which is above the right side 6.click the log out option
Env: Production
Module: Logout
Severity: Minor
Screenshort
Expected:The user remains logged in on other devices
Responsible QA: Rokaiya zaman suthi
Bug Reporting
# SL 03
Issue: Verify that users can place orders without creating an account
Reproducing Steps:
1.Go to URL: https://shorturl.at/ceg0x 2.Click on the login button in the right side on the above. 3.Click log in button and give information then press continue. 4.We will get the home page 5. Above the middle of the home page 6.We will get search bar 7.Search the required food then select the food and make payment
Env: Production.
Module: Ordering workflow
Severity: Minor
Screenshort
Expected:Users cannot place orders without creating an account
Responsible QA:Rokaiya zaman suthi

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (176/176)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (12/176)*100 = 7%
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (161/176)*100 = 91%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (3/176)*100 = 2%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/176)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A